## Project Budget Summary
Guam Southern Flood Mitigation Project
| Available | 0
|  | Design | Construction | Notes
PM @ 5% |  | 0 | 0 | I think it is safe to say that this will be a high involvement project.
Engineering 35% P&S (In-hse)
| ECT | 60000 | 10000 | No fee received, estimate only
| AE Serv | 40000 |  | Typical
| Cost | 27000 |  | Estimate received
| Geotech | 115000 |  | Estimate received. No post award fee provided.
Contracting |  | 30000 |  | Typical
Environmental |  | 310000 | 10000 | Estimate plus assumed post involvement. May come down with more info.
Cultural |  | 77720 | 135058 | Estimate plus assumed post involvement. May come down with more info.
AE Contract 35% - Final |  |  |  | 10% of ECC. Assumes POH does all Enviro/Cultural coordination and documentation.
| AE | 95000 |  | Estimate by professional engineer
| Construction |  | 950000 | Seems a bit high for the anticipated work
| Geotech | 177000 |  | Estimate received. No post award fee provided.
S&A @ 11% |  | 104500
Totals |  | 1036220 | 1105058 | 2141278

## ENV Schedule
Task | Days | Start | End | BiOp Contingency | Hours | DQC hours
Contract starts (7600A signed) | 0 | 2025-11-01
Contract Coordination Meeting | 7 | 2025-11-01 | 2025-11-08 |  | 8 | 4
Study kickoff Meeting | 4 hours | 2025-11-08 | 2025-11-13 |  | 24 | 4
Resource Agency Coordination Letters & Meeting | 7 | 2025-11-01 | 2025-11-08 |  | 24 | 8
Surveys (FWCA, terrestrial ESA species) |  |  |  |  | 12 | 4 | 70000
ESA Section 7
initiate ESA coordination w/ USFWS & NMFS | 7 | 2025-11-01 | 2025-11-08 |  | 8 | 1
initate MBTA coordination w/ USFWS | 7 | 2025-11-01 | 2025-11-08 |  | 8 | 1
initiate coordination w/ SHPD | 7 | 2025-11-01 | 2025-11-08 |  | 8 | 1
Cultural Resources review w/ SHPD | 30 | 2025-11-08 | 2025-12-08
ESA section 7 Biological evaluation for USFWS & NMFS | 14 | 2025-11-01 | 2025-11-15 |  | 40 | 24
Consultation letters signed by who? | 7 | 2025-11-15 | 2025-11-22 |  | 5 | 1
transmit consultations | 1 | 2025-11-22 | 2025-11-23 |  | 4
USFWS & NMFS review & concurrence | 30 | 2025-11-23 | 2025-12-23
If USFWS or NMFS finds "likely to adversely affect" = Biological Opinion | 180 | 2025-12-23 | 2026-06-21 | Then Mitigated FONSI with these dates
EFH
EFH Assessment for NMFS | 14 | 2025-11-16 | 2025-11-30 |  | 40 | 24 | Predecessors: Past, yet still current survey of the area or Current survey results and DOPAA
Consultation letters signed by who? | 7 | 2025-11-23 | 2025-11-30 |  | 5 | 1
transmit consultations | 1 | 2025-11-24 | 2025-11-25 |  | 4
MSA EFH consultation with NMFS | 70 | 2025-12-24 | 2026-03-04 |  | 40 | 24
Dredging & Filling Compliance
Rivers and Harbors Act Section 10 | 14 | 2025-12-01 | 2025-12-15 |  | 40 | 24
MPRSA Section 103 assessment for ocean disposal | 14 | 2025-12-16 | 2025-12-30 |  | 40 | 24
CWA Section 404(b)(1) analysis | 14 | 2025-12-31 | 2026-01-14 |  | 40 | 24
CWA Section 404 Permit
CWA NPDES Permits
CZMA
CZMA Federal Consistency Assessment | 14 | 2026-01-15 | 2026-01-29 |  | 40 | 24
Consultation letters signed by who? | 7 | 2026-01-30 | 2026-02-06 |  | 5 | 1
transmit consultations | 1 | 2026-02-07 | 2026-02-08 |  | 4
CZMA Federal Consistency Review | 30 | 2025-11-23 | 2025-12-23 | 2026-06-22
Greenhouse Gas Emissions? | 14 | 2025-11-22 | 2025-12-06 |  | 24 | 8
Environmental Justice? | 14 | 2025-12-06 | 2025-12-20 |  | 24 | 8
Public Scoping Meeting? | 7 | 2025-12-20 | 2025-12-27 |  | 24 | 8
Write the EA | 30 | 2025-12-27 | 2026-01-26 | 2026-07-22 | 160
Internal USACE DQC review | 14 | 2026-01-26 | 2026-02-09 | 2026-08-05 |  | 32
Draft 1: OIA / BSP Draft Review | 30 | 2026-02-09 | 2026-03-11 | 2026-09-04
Revise | 14 | 2026-03-11 | 2026-03-25 | 2026-09-18 | 40 | 24
Draft 2: Public Review | 30 | 2026-03-25 | 2026-04-24 | 2026-10-18 | 8 | 2
Prepare final EA / Final DQC | 14 | 2024-05-17 | 2024-05-31 | 2026-11-01 | 40 | 24
Draft 3: OIA / BSP reviews Final Draft EA | 30 | 2024-06-01 | 2024-07-01 | 2026-12-01
FONSI – signed by OIA Senior Level Action Proponent | 30 | 2024-07-02 | 2024-08-01 | 2026-12-31 | 4 | 4
[5 empty] | 723 | 304
Formulas:
Start = [End, row above]
Start = [Start, row above]
End = [Start]+7
End = [Start]+[Days]
BiOp Contingency = E33+[Days]
BiOp Contingency = [BiOp Contingency, row above]+[Days]
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I bumped this up to 8 to include work at the desk for due outs from initial meeting
Note on F7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I added hours for scope negotiation
Note on H19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lets add relevant predecessors so we are clear that accomplishing env task(s) is contingent upon pertinent and timely info.
Note on A23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Since this is IIS, we would be drafting the DA permit application for OIA or BSP to submit to regulatory and need to account for that time under task 27 and eliinate task 24 as it is part of the permit application. We do not traditionally submit a Section 404(b)(1) analysis in the DA permit application; traditionally this is the responsibility of Regulatory to do so I would eiliminate the 404(b)(1) task. This section should more accurately represent applying for a permit. And in this case, if there is a 404 discharge, then we should also be preparing a Section 401 WQC application for which I have no experience to advise on the scope or timeline associated with a W!C application in Guam. Likewise I cannot advise on the timeline for a 402 permit application, but I know Jessica podoski recently prepared and submitted to Guam for Agana SBH O&M repairs and noted significant differences btwn the Hawaii State and USEPA (Guam) offices for 402 and she could better advise on required time.
Note on A25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Does red text denote an option? I did not hear mention of ocean disposal associated with this action as it appears BSP wants to dredge and beneficially reuse for bank stabilization. In that case, Section 103 would not be applicable. Please advise.
Note on G34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recommend eliminating dqc hours for GHG, EJ and public scoping mtg. These should be accounted for in dqc of the nepa doc
Note on F44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added time for routing/transmittal/briefing/coordination for signature

## ENV Budget
| Estimated Rate | Estimated Hours | Estimate
Project Manager | 192 | 260 | 49920
Senior Environmental Planner (DQC Review) | 192 | 304 | 58368
Junior Environmental Planner (NEPA) | 164 | 723 | 118572
Archaeologist | 186 | 25 | 4650
Administrative | 192 | 30 | 5760
Contracting (Set Fee) |  |  | 40000
12% Contingency |  |  | 50000
Total In-House & Contracted Labor Estimate |  |  | 327270
$500K

## GEO Hours Breakdown
PROJECT: Southern Guam Flood Mitigation |  | CEPOA-ENG-M : J4L0GTS
Task ID | Task Name | Junior Engineer | Senior Engineer | Section Chief | Assumptions
0 | Grand Total | 346 | 205 | 55
1 | 15% Design Concept Development | 198 | 117 | 26
1.1 | PDT Meetings (bi-weekly for 12 months) | 26 | 10 | 10
1.2 | Desktop Study for 15% concept | 20 | 5 | 0
1.3 | 15% Design Analysis | 40 | 10 | 8 | Prelimenary design analysis to ensure feasibility of proposed concept design and to ensure the AE will have an undestanding of design intentions
1.4 | Geotechnical Design Documentation Report | 40 | 20 | 8 | 15% design concept to contain mock ups of proposed design
1.5 | Umatac Site Visit | 72 | 72 | 0 | Site visit to perform prelimenary geotechnical site investigation and identify site conditions for 15% concept design
2 | 15% Design Concept Review | 28 | 16 | 9
2.1 | 15% Design Review | 16 | 8 | 1
2.2 | 15% Design Review Conference | 4 | 4 | 0
2.3 | 15% Design DQC | 8 | 4 | 8
3 | A/E RFP to Complete Design | 80 | 40 | 15
3.1 | RFP Input | 40 | 20 | 10
3.2 | Contracting Actions | 40 | 20 | 5
4 | Pre-Final Design (90-95%) thru Rev Conf | 28 | 12 | 3
4.1 | 95% Design Review | 20 | 8 | 2
4.2 | 95% Design Review Conference | 8 | 4 | 1
5 | Design Complete (Reviewed 100%) | 12 | 20 | 2
5.1 | 100% Design Review | 8 | 16 | 2
5.2 | 100% Design Review Conference | 4 | 4 | 0
| Government Fully Burdened Rates (estimated) | 160 | 180 | 180
| Government Subtotals | 55360 | 36900 | 9900 | 102160
Government Misc. Costs
| Line Item | Value
| Site Visit - per diem ($283/day) and airfare (2 geotech, 6 days) | 11396
| Preliminary Site Investigation (supplies and soil testing) | 7500
| Rental Car (1 car) | 600
|  |  |  | Gov Total Cost | 114156
A/E Contract Estimate |  | CEPOA-ENG-M : J4L0GTS
Task ID | Task Name | Junior Engineer | Senior Engineer | Principal Engineer | Assumptions
0 | Grand Total | 460 | 159 | 59
1 | AE Geotechnical Investigation | 196 | 74 | 20
1.1 | Coordination (Meetings, Working with other disciplines) | 40 | 10 | 10
1.2 | Field Prep, Permits, and Coordination for Drilling | 40 | 8 | 2
1.3 | Geotechnical Field Investigation (3 days) | 36 | 36 | 4 | Geotech Field Investigation to be 3 days long (4-20 ft borings, revetment length unknown at the moment, # of bornings will be scaled with length) w/ two USACE personnel logging.
1.4 | Geotechnical Data Report | 80 | 20 | 4
2 | 95% Design + Plans and Specs Development | 220 | 65 | 30
2.1 | Review 15% Design Concept | 20 | 5 | 5
2.2 | Geotechnical Analysis for MSE Wall | 40 | 20 | 5
2.3 | Draft Geotechnical Design Documentation Report | 60 | 20 | 10
2.4 | Plans and Specs Development and Coordination | 100 | 20 | 10
3 | Pre-Final Design (90-95%) thru Rev Conf | 10 | 6 | 3
3.1 | 95% Design Review | 2 | 2 | 1
3.2 | 95% Design Review Conference | 8 | 4 | 2
4 | Design Complete (Reviewed 100%) | 34 | 14 | 6
4.1 | Final Geotechnical Design Documentation Report | 30 | 10 | 5
4.2 | 100% Design Review Conference | 4 | 4 | 1
| AE Fully Burdened Rates (estimated) | 160 | 220 | 300
| AE Subtotals | 73600 | 34980 | 17700 | 126280
AE Misc. Costs | [5 empty] | ft
| Line Item | Value
| Drilling Services = (4) 20ft BH | 40000
| Laboratory Testing | 10000
|  |  |  | AE Total Cost | 176280
|  |  |  | Gov + AE Contract Cost | 290436

## COST FY'25
ORG SCOPE OF WORK - RESOURCE BREAKDOWN | [9 empty] | Cost Engineering
PROGRAM / STUDY: | [6 empty] | PROGRAM MANAGER |  |  | PROJECT NO: |  | FUNDED WI:
PROJECT TITLE: | [6 empty] | PROJECT MANAGER |  |  | DATE PREPARED:
Umatac River Maintenance and Bank Stabilization | [6 empty] | 0 |  |  | 0
CHIEF / SUPERVISOR: |  |  | REVIEW/APPROVAL: |  | OFFICE: |  | PM REVIEW/APPROVAL: |  |  | REVISION NO: |  | ORG CODE:
Michael P. Jacobs |  |  |  |  | NWW EC-E | [6 empty] | G4L1X00
SHORT TASK DESCRIPTION |  |  | PHASE: | FISCAL YR: | BUDGET PREPARED BY:
FY25
Organization Activity Scope:
Priority Project 1. Umatac River Maintenance and Bank Stabilization
Schedule of Activity:
|  |  | Estimated Start |  |  | Est / Sch Duration (Work Days) | [5 empty] | Estimated End
| Notes: |  |  |  | 20.5 | Budgeted Mandays (calculated)
In-house Labor (LABOR):
| GRADE |  | TITLE |  |  | HOURS see next page |  | BURDEN RATE |  |  | LABOR
| GS-14 ATR |  | ATR |  |  | 0 | # Hours |  | per hour |  | 0
| GS-13 LEAD |  | Cost Lead Engineer |  |  | 114 | # Hours | 162 | per hour |  | 18468
| GS-13 LEAD |  | Senior Cost Engineer |  |  | 50 | # Hours | 170 | per hour |  | 8500
| GS-12 |  | Senior Cost Engineer |  |  | 0 | # Hours | 111 | per hour |  | 0
| GS-11 |  | Cost Engineer |  |  | 0 | # Hours | 80 | per hour |  | 0
| GS-11 |  | Cost Engineer |  |  | 0 | # Hours | 80 | per hour |  | 0
| GS-09 CADD |  | Technician |  |  | 0 | # Hours | 70 | per hour |  | 0
| GS-07 |  | Engineering Intern |  |  | 0 | # Hours | 55 | per hour |  | 0
| GS-05 GEN |  | Admin Assist |  |  | 0 | # Hours | 45 | per hour |  | 0
| Section Chief (supervisor) |  |  |  | 0% | 0 | # Hours | 153 | per hour |  | 0
[5 empty] | Total hours | 164
[8 empty] | Weighted Average Rate per hour | 164.439 |  | Sub-Total | 26968
In-house Services (SHOP/FACIL):
| Vehicles |  | (VEHSVCLMO) |  |  |  | # Days | 55 | Per Day |  | 0
| Other | [5 empty] | # ___ | 0 | LS |  | 0
[11 empty] | Sub-Total | 0
Travel (TRAVEL):
| Per Diem | [5 empty] | # Days | 144 | Per Day |  | 0
| Vehicle | [5 empty] | #Times | 250 | Each |  | 0
| Flight | [5 empty] | #Trips | 1685.3 | Per Trip |  | 0
| Local Travel | [6 empty] | 0 | LS |  | 0
| Miscellaneous |  | hotel taxes/luggage |  |  |  |  | 0 | LS |  | 0
[11 empty] | Sub-Total | 0
Technical Writer/Editor (TIP) and Reprographics (PRINTING):
| Writer/Editor |  | (IT-TIP-GRA) |  |  | 0 | # Hours | 42 | per hour |  | 0
| Reprographics |  | (PRINT-DAPS) | [5 empty] | LS |  | 0
[11 empty] | Sub-Total | 0
A/E Contracts (AESVCS) | [8 empty] | LS |  | Sub-Total | 0
Supply/Service Contracts (CONSTSVCS) | [8 empty] | LS |  | Sub-Total | 0
Graphic design/CD (IT) | [8 empty] | LS |  | Sub-Total | 0
MIPR | [8 empty] | LS |  | Sub-Total | 0
[7 empty] | TOTAL ACTIVITY BUDGET |  |  |  |  | 26968
WORK ACTIVITY DESCRIPTION |  |  |  |  | GS-14 ATR | GS-13 LEAD | GS-13 LEAD | GS-12 | GS-11 | GS-11 | GS-09 CADD | GS-07 | GS-05 GEN
|  | TOTALS HOURS |  |  | 0 | 114 | 50 | 0 | 0 | 0 | 0 | 0 | 0
Initial Estimate | [5 empty] | 40 | 24
Final Estimate | [5 empty] | 40 | 16
IGE | [5 empty] | 24 | 8
TPCS | [5 empty] | 10 | 2
Formulas:
PROJECT NO: = [3]Cover!K5
Print All
Print All
Print
Print
Print All
Print

## Step 4 (compliance) budget
Step 1 - Southern Guam Flood Mitigation Project (D23AP00124-00) | 2024-08-30 |  | POA Archaeologist | Fully Burdened Rate
Cultural Resources Support - COST ESTIMATE |  |  | Laura Stelson | 113
Lead: Laura Stelson |  |  | Tyler Teese | 130
|  |  | Mike Rouse (Chief) | 168
Assumptions:
No previous archaeological survey in project area
Archaeological investigations will be carried out by archaeologists
Determination of potential adverse effect to properties; agreement document is required
Bi-weekly meeting participation will be required for duration of project phase
[5 empty] | Travel & Per Diem | [5 empty] | Contracts & Miscellaneous
Task | Labor Hours | Labor Days | Cost | Milestone Total | Item | Day | Max Rate | /Unit | Cost |  | Item | Max Rate | /Unit | Cost
1. GHPO Request for Assistance & Literature Review |  |  |  | Total | Per Diem | 8 | 281 | /day | 4496 |  | GPS Rental | 750 | 1 | 750
Archaeologist Lead | 16 | 2 | 1808 |  | Airfare |  | 3000 | /trip | 6000 |  | Miscillaneous supplies | 200 | 2 | 400
Archaeologist Support | 6 | 0.75 | 780 |  | Vehicle Rental | 5 | 100 | /day | 500 |  | Baggage fees | 40 | 4 | 160
|  |  |  | 2588 | [5 empty] | 10996 | Gas | 5 | 40 | 200
1150
2. Section 106 Notification Letter (Identify APE)
Archaeologist Lead | 8 | 1 | 904
Archaeologist Support | 4 | 0.5 | 520
Chief Review | 2 | 0.25 | 336
1760
3. Draft research design
Archaeologist Lead | 10 | 1.25 | 1130
Archaeologist Support | 4 | 0.5 | 520
Chief Review | 2 | 0.25 | 336
1986
4. Archaeological Survey
Archaeologist Lead | 40 | 4 | 4520
Archaeologist Support | 40 | 4 | 5200
9720
5. Photolog
Archaeologist Lead | 3 | 0.375 | 339
Archaeologist Support | 1.5 | 0.1875 | 195
534
6. ArcGIS Geodatabase
Archaeologist Lead | 10 | 1.25 | 1130
Archaeologist Support | 2 | 0.25 | 260
1390
7. Draft Survey Report
Archaeologist Lead | 80 | 10 | 9040
Archaeologist Support | 20 | 2.5 | 2600
Chief Review | 4 | 0.5 | 672
12312
8. Section 106 Assessment Letter (Finding of Effect)
Archaeologist Lead | 24 | 3 | 2712
Archaeologist Support | 8 | 1 | 1040
Chief Review | 2 | 0.25 | 336
4088
9. Section 106 Agreement Document (MOA/PA)
Archaeologist Lead | 120 | 15 | 13560
Archaeologist Support | 24 | 3 | 3120
Chief Review | 8 | 1 | 1344
18024
10. Meetings
Archaeologist Lead | 40 | 5 | 4520
Archaeologist Support | 20 | 2.5 | 2600
Chief | 8 | 1 | 1344
8464
LABOR TOTAL | 506.5 | 61.3125 |  | 60866 | TOTAL TRAVEL & PER DIEM |  |  |  |  | 10996 | TOTAL CONTRACTS & MISC. |  |  |  | 1510
TOTAL COST |  |  |  | 73372

## Step 7 (contracting prep) budge
Step 7 - Southern Guam Flood Mitigation Project (D23AP00124-00) | 2024-08-30 |  | POA Archaeologist | Fully Burdened Rate
Cultural Resources Support - COST ESTIMATE |  |  | Laura Stelson | 113
Lead: Laura Stelson |  |  | Tyler Teese | 130
|  |  | Mike Rouse (Chief) | 168
Task | Labor Hours | Labor Days | Cost | Milestone Total
1. Contract review & additions |  |  |  | Total
Archaeologist Lead | 16 | 2 | 1808
Archaeologist Support | 6 | 0.75 | 780
Chief review | 4 | 0.5 | 672
2588
2. Meetings
Archaeologist Lead | 8 | 1 | 904
Archaeologist Support | 4 | 0.5 | 520
Chief | 2 | 0.25 | 336
1760
LABOR TOTAL | 40 | 5 |  | 4348
TOTAL COST |  |  |  | 4348

## Steb 9b (stabilization) budget
Step 79b- Southern Guam Flood Mitigation Project (D23AP00124-00)
Archaeological Monitoring
Assumptions:
1. Assume 6 weeks of on site monitoring during stream bank stabilization
2. Construction will occur 8 hours per day
3. Archaeological monitor will work 10-hour shifts (8 hours at construction site, 2 hours for safety meetings, paperwork, etc.)
4. Archaeological monitor will stay at local hotel and have per diem
5. Assume 2 days travel to and from Guam; 44 days on island
Monitoring Plan | Cost/Hour | Hour Estimate | Cost
Contractor Archaeologist | 150 | 40 | 6000
Contractor PM Review | 160 | 8 | 1280
Task Total: |  | 48 | 7280
Monitoring Labor | Cost/Hour | Hour/ Day Estimate | Cost
Contractor Archaeologist | 150 | 460 | 69000
Per Diem | 283 | 46 | 13018
Flight (HNL - GUM) | - | - | 3000
Task Total: |  | 460 | 85018
Monitoring Report | Cost/Hour | Hour Estimate | Cost
Contractor Archaeologist | 150 | 120 | 18000
Contractor PM Review | 160 | 30 | 4800
Task Total: |  | 150 | 22800
Contractor Admin Profit (10% of total cost) | Total Cost | % Increase | Cost
| 115098 | 10 | 11509.8
USACE Archaeologist Review | Cost/Hour | Hour Estimate | Cost
SOW Development | 130 | 25 | 3250
Monitoring Plan | 130 | 20 | 2600
Monitoring Report | 130 | 20 | 2600
Contract Support | 130 | 20 | 2600
Task Total: |  | 65 | 8450
TOTAL COST: |  |  | 135057.8